## Draft 1
|  |  |  | September |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April
Overall Task | Specific Task | Responsibility | Status | 22-28 | 29- Oct 5th | 2019-06-12 | 13-19 | 20-26 | 27-Nov 2nd | 2019-03-09 | 2019-10-16 | 17-23 | 24-30 | 2019-01-07 | 2019-08-14 | 15-21 | 22-28 | 29-Jan4th | 2019-05-11 | 2019-12-18 | 19-25 | 26-Feb1st | 2019-02-08 | 2019-09-15 | 16-22 | 23-29 | 2019-01-07 | 2019-08-14 | 15-21 | 22-28 | 29-Apr4th | 2019-05-11 | 2019-12-18 | 19-25 | 26-30
1. Project Selection |  | All | Complete
2.Project Proposal | a. Problem Statement | Sarah | Complete
| b. Project Obj. | Sarah
| c. Background | Ruhmaa
| d. Methodology | Alex
| e. Gantt Chart | Zoee
| f. Project Tasks | Zoee
| g. Prelim. Budget | Ruhmaa
3. CSA Visit | Attend PDR if possible | All | Complete
4. Project Review |  | All | Not Completed
5. Progress Report |  | All | Not Completed | bar: November 2019-03-09 to November 24-30
6. Order all Components |  | All | Not Completed | bar: December 2019-01-07
7. First iteration- Filter Design |  | All | Not Completed | bar: December 2019-08-14 to December 22-28
8. Analysis and Test Plan |  | All | Not Completed
9.2nd-nth iteration |  | All | Not Completed
10. Combine all filters |  | All | Not Completed
11. Combine the GND Station with other teams |  | All | Not Completed
7. Project Demo |  | All | Not Completed
8. Project Presentation |  | All | Not Completed
9. Final Project Report |  | All | Not Completed

## Printable
Overall Task | Specific Task | Responsibility | Status | Sept |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | March
|  |  |  | 22-28 | 29-5th | 2019-06-12 | 13-19 | 20-26 | 27-2nd | 2019-03-09 | 2019-10-16 | 17-23 | 24-30 | 2019-01-07 | 2019-08-14 | 15-21 | 22-28 | 29-4th | 2019-05-11 | 2019-12-18 | 19-25 | 26-1st | 2019-02-08 | 2019-09-15 | 16-22 | 23-29 | 2019-01-07 | 2019-08-14 | 15-21 | 22-28 | 29-Apr4th
1. Project Selection |  | All | Complete | bar: Sept 22-28
2.Project Proposal | a. Problem Statement | Sarah | Complete | bar: Oct 2019-06-12
| b. Project Obj. | Sarah
| c. Background | Ruhmaa
| d. Methodology | Alex
| e. Gantt Chart | Zoee
| f. Project Tasks | Zoee
| g. Prelim. Budget | Ruhmaa
3. CSA Visit | Attend PDR if possible | All | Complete | bar: Oct 2019-06-12
4. Project Review |  | All | Not Completed | bar: Oct 13-19 to Oct 20-26
5. Progress Report |  | All | Not Completed | bar: Oct 27-2nd to Nov 24-30
6. Order all Components |  | All | Not Completed | bar: Dec 2019-01-07
7. First iteration- Filter Design |  | All | Not Completed | bar: Dec 2019-08-14 to Jan 2019-12-18
8. Analysis and Test Plan |  | All | Not Completed | bar: Jan 2019-12-18
9.2nd-nth iteration |  | All | Not Completed | bar: Jan 19-25 to Feb 2019-02-08
10. Combine all filters |  | All | Not Completed | bar: Feb 2019-09-15 to Feb 16-22
11. Combine the GND Station with other teams |  | All | Not Completed | bar: Feb 23-29 to March 2019-08-14
7. Project Demo |  | All | Not Completed | bar: March 2019-08-14
8. Project Presentation |  | All | Not Completed | bar: March 15-21
9. Final Project Report |  | All | Not Completed | bar: March 22-28